## Project Management Plan
Quarter | Date | Project Deploy Webserver to Azure | Difficulty Level
Q1 - 2023 | 2023-01-01 | Create Packer file | Medium
| 2023-01-14 | Create and Execute Terraform file | Hard
| 2023-02-28 | Deploy Webserver to Virtual Machine using packer and terraform | Medium
Project Deploy CI\CD Pipelines
Q2 - 2023 | 2023-05-01 | Spreadsheet planning | Medium
| 2023-05-10 | Create Trello | Medium
| 2023-05-20 | Create Git Repo | Medium
| 2023-06-01 | Create the Cloud-Based Development Environment | Hard
| 2023-06-10 | Clone Project in Azure Portal using cloud shell | Medium
| 2023-07-15 | Local App Test | Medium
| 2023-07-18 | SetUp Github Actions | Medium
| 2023-07-23 | Replace yml code | Medium
| 2023-08-01 | Verify Remote Tests for App pass | Medium
| 2023-08-15 | Setup Azure Pipelines for CI | Hard
| 2023-08-20 | Create Release for Azure Pipelines | Hard
| 2023-08-23 | Making predictions to get result | Medium
| 2023-08-30 | Demo the whole project | Medium
Project: Ensuring Quality Releases
Q2 - 2023 | 01 Sept 23 - 31 Dec 23 | Submit Project 3 | Medium
| Goal | To finish all the project on time