## Project Management Plan
Week | Project Building CI/CD Pipeline | Effort
2023-06-01 | Spreadsheet planning | 1 h
| Create Trello | 3 h
| Create Git Repo | 4 h
2023-06-10 | Create the Cloud-Based Development Environment | 5 h
| Clone Project in Azure Portal using cloud shell | 2 h
| Local App Test | 1 h
| SetUp Github Actions | 1 h
2023-06-15 | Replace yml code | 3 h
| Verify Remote Tests for App pass | 1 h
| Setup Azure Pipelines for CI | 3 h
| Create Release for Azure Pipelines | 3 h
2023-06-22 | Making predictions to get result | 1 h
| Demo the whole project | 6 h
Goal | Build a CI CD pipeline with automated trigger when any change is done on the git repo